## Project Parameters
[Company Name]
Project Report
[Date]
Shaded cells are calculated for you. You do not need to enter anything into them.
Project type | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administration staff | Total
Business continuity planning | 10% | 20% | 40% | 10% | 10% | 10% | 100%
Business process re-engineering | 10% | 10% | 10% | 50% | 10% | 10% | 100%
Cost reduction | 10% | 20% | 10% | 20% | 30% | 10% | 100%
Process improvement | 10% | 20% | 10% | 40% | 10% | 10% | 100%
Sarbanes-Oxley | 10% | 20% | 20% | 20% | 20% | 10% | 100%
Strategic planning | 10% | 10% | 50% | 0% | 20% | 10% | 100%
Blended rates | 250 | 225 | 200 | 175 | 150 | 50

## Planning
[Company Name]
Project Report
Company Confidential
Project name | Project type | Estimated start | Estimated finish | Estimated work | Duration
A. Datum Corporation | Business continuity planning | 2005-01-04 | 2005-03-04 | 200 | 60
Adventure Works | Business continuity planning | 2005-01-20 | 2005-02-21 | 400 | 31
Alpine Ski House | Business process re-engineering | 2005-02-06 | 2005-04-16 | 500 | 70
Baldwin Museum of Science | Business process re-engineering | 2005-02-24 | 2005-04-25 | 150 | 61
Blue Yonder Airlines | Cost reduction | 2005-03-08 | 2005-03-18 | 250 | 10
City Power & Light | Cost reduction | 2005-03-19 | 2005-04-29 | 300 | 40
Coho Vineyard | Cost reduction | 2005-04-10 | 2005-04-20 | 500 | 10
Coho Winery | Cost reduction | 2005-04-18 | 2005-05-12 | 750 | 24
Coho Vineyard & Winery | Cost reduction | 2005-05-12 | 2005-06-22 | 450 | 40
Contoso, Ltd. | Cost reduction | 2005-05-23 | 2005-07-21 | 250 | 58
Contoso Pharmaceuticals | Cost reduction | 2005-06-14 | 2005-08-12 | 200 | 58
Consolidated Messenger | Cost reduction | 2005-06-30 | 2005-08-30 | 180 | 60
Fabrikam, Inc. | Process improvement | 2005-01-16 | 2005-08-15 | 250 | 209
Fourth Coffee | Process improvement | 2005-07-17 | 2005-09-01 | 240 | 44
Graphic Design Institute | Process improvement | 2005-07-25 | 2005-09-30 | 320 | 65
Humongous Insurance | Sarbanes-Oxley | 2005-08-01 | 2005-10-01 | 550 | 60
Litware, Inc. | Sarbanes-Oxley | 2005-08-20 | 2005-10-02 | 350 | 42
Lucerne Publishing | Sarbanes-Oxley | 2005-09-02 | 2005-11-12 | 200 | 70
Margie's Travel | Sarbanes-Oxley | 2005-09-12 | 2005-11-25 | 220 | 73
Northwind Traders | Sarbanes-Oxley | 2005-10-12 | 2005-12-20 | 600 | 68
Proseware, Inc. | Strategic planning | 2005-10-24 | 2005-12-14 | 525 | 50
School of Fine Art | Strategic planning | 2005-11-04 | 2005-11-24 | 180 | 20
TOTAL |  |  |  | 7565

## Tracking
[Company Name]
Project Report
Company Confidential
Project name | Actual start | Actual finish | Actual work | Actual duration
A. Datum Corporation | 2005-01-04 | 2005-03-09 | 220 | 65
Adventure Works | 2005-01-25 | 2005-02-28 | 390 | 33
Alpine Ski House | 2005-02-10 | 2005-04-23 | 500 | 73
Baldwin Museum of Science | 2005-02-22 | 2005-04-29 | 145 | 67
Blue Yonder Airlines | 2005-03-09 | 2005-03-28 | 255 | 19
City Power & Light | 2005-03-19 | 2005-05-05 | 310 | 46
Coho Vineyard | 2005-04-12 | 2005-04-27 | 510 | 15
Coho Winery | 2005-04-17 | 2005-05-16 | 790 | 29
Coho Vineyard & Winery | 2005-05-15 | 2005-06-24 | 430 | 39
Contoso, Ltd. | 2005-05-24 | 2005-07-24 | 235 | 60
Contoso Pharmaceuticals | 2005-06-16 | 2005-08-16 | 235 | 60
Consolidated Messenger | 2005-07-02 | 2005-09-25 | 190 | 83
Fabrikam, Inc. | 2005-01-18 | 2005-08-16 | 230 | 208
Fourth Coffee | 2005-07-19 | 2005-09-15 | 225 | 56
Graphic Design Institute | 2005-07-26 | 2005-10-20 | 305 | 84
Humongous Insurance | 2005-08-01 | 2005-10-14 | 565 | 73
Litware, Inc. | 2005-08-28 | 2005-10-21 | 350 | 53
Lucerne Publishing | 2005-09-04 | 2005-11-15 | 205 | 71
Margie's Travel | 2005-09-13 | 2005-11-29 | 230 | 76
Northwind Traders | 2005-10-22 | 2005-12-24 | 560 | 62
Proseware, Inc. | 2005-10-14 | 2005-12-10 | 540 | 56
School of Fine Art | 2005-11-04 | 2005-11-20 | 190 | 16
TOTAL |  |  | 7610

## Planned Totals
[Company Name]
Project Report
Company Confidential
Project name | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administration staff | Total
A. Datum Corporation | 5000 | 9000 | 16000 | 3500 | 3000 | 1000 | 37500
Adventure Works | 10000 | 18000 | 32000 | 7000 | 6000 | 2000 | 75000
Alpine Ski House | 12500 | 11250 | 10000 | 43750 | 7500 | 2500 | 87500
Baldwin Museum of Science | 3750 | 3375 | 3000 | 13125 | 2250 | 750 | 26250
Blue Yonder Airlines | 6250 | 11250 | 5000 | 8750 | 11250 | 1250 | 43750
City Power & Light | 7500 | 13500 | 6000 | 10500 | 13500 | 1500 | 52500
Coho Vineyard | 12500 | 22500 | 10000 | 17500 | 22500 | 2500 | 87500
Coho Winery | 18750 | 33750 | 15000 | 26250 | 33750 | 3750 | 131250
Coho Vineyard & Winery | 11250 | 20250 | 9000 | 15750 | 20250 | 2250 | 78750
Contoso, Ltd. | 6250 | 11250 | 5000 | 8750 | 11250 | 1250 | 43750
Contoso Pharmaceuticals | 5000 | 9000 | 4000 | 7000 | 9000 | 1000 | 35000
Consolidated Messenger | 4500 | 8100 | 3600 | 6300 | 8100 | 900 | 31500
Fabrikam, Inc. | 6250 | 11250 | 5000 | 17500 | 3750 | 1250 | 45000
Fourth Coffee | 6000 | 10800 | 4800 | 16800 | 3600 | 1200 | 43200
Graphic Design Institute | 8000 | 14400 | 6400 | 22400 | 4800 | 1600 | 57600
Humongous Insurance | 13750 | 24750 | 22000 | 19250 | 16500 | 2750 | 99000
Litware, Inc. | 8750 | 15750 | 14000 | 12250 | 10500 | 1750 | 63000
Lucerne Publishing | 5000 | 9000 | 8000 | 7000 | 6000 | 1000 | 36000
Margie's Travel | 5500 | 9900 | 8800 | 7700 | 6600 | 1100 | 39600
Northwind Traders | 15000 | 27000 | 24000 | 21000 | 18000 | 3000 | 108000
Proseware, Inc. | 13125 | 11812.5 | 52500 | 0 | 15750 | 2625 | 95812.5
School of Fine Art | 4500 | 4050 | 18000 | 0 | 5400 | 900 | 32850
TOTAL Cost | 189125 | 309937.5 | 282100 | 292075 | 239250 | 37825 | 1350312.5
TOTAL Hours | 756.5 | 1377.5 | 1410.5 | 1669 | 1595 | 756.5 | 7565

## Actual Totals
[Company Name]
Project Report
Company Confidential
Project name | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administration staff | Total
A. Datum Corporation | 5500 | 9900 | 17600 | 3850 | 3300 | 1100 | 41250
Adventure Works | 9750 | 17550 | 31200 | 6825 | 5850 | 1950 | 73125
Alpine Ski House | 12500 | 11250 | 10000 | 43750 | 7500 | 2500 | 87500
Baldwin Museum of Science | 3625 | 3262.5 | 2900 | 12687.5 | 2175 | 725 | 25375
Blue Yonder Airlines | 6375 | 11475 | 5100 | 8925 | 11475 | 1275 | 44625
City Power & Light | 7750 | 13950 | 6200 | 10850 | 13950 | 1550 | 54250
Coho Vineyard | 12750 | 22950 | 10200 | 17850 | 22950 | 2550 | 89250
Coho Winery | 19750 | 35550 | 15800 | 27650 | 35550 | 3950 | 138250
Coho Vineyard & Winery | 10750 | 19350 | 8600 | 15050 | 19350 | 2150 | 75250
Contoso, Ltd. | 5875 | 10575 | 4700 | 8225 | 10575 | 1175 | 41125
Contoso Pharmaceuticals | 5875 | 10575 | 4700 | 8225 | 10575 | 1175 | 41125
Consolidated Messenger | 4750 | 8550 | 3800 | 6650 | 8550 | 950 | 33250
Fabrikam, Inc. | 5750 | 10350 | 4600 | 16100 | 3450 | 1150 | 41400
Fourth Coffee | 5625 | 10125 | 4500 | 15750 | 3375 | 1125 | 40500
Graphic Design Institute | 7625 | 13725 | 6100 | 21350 | 4575 | 1525 | 54900
Humongous Insurance | 14125 | 25425 | 22600 | 19775 | 16950 | 2825 | 101700
Litware, Inc. | 8750 | 15750 | 14000 | 12250 | 10500 | 1750 | 63000
Lucerne Publishing | 5125 | 9225 | 8200 | 7175 | 6150 | 1025 | 36900
Margie's Travel | 5750 | 10350 | 9200 | 8050 | 6900 | 1150 | 41400
Northwind Traders | 14000 | 25200 | 22400 | 19600 | 16800 | 2800 | 100800
Proseware, Inc. | 13500 | 12150 | 54000 | 0 | 16200 | 2700 | 98550
School of Fine Art | 4750 | 4275 | 19000 | 0 | 5700 | 950 | 34675
TOTAL Cost | 190250 | 311512.5 | 285400 | 290587.5 | 242400 | 38050 | 1358200
TOTAL Hours | 761 | 1384.5 | 1427 | 1660.5 | 1616 | 761 | 7610